## Inventory
Form Name | Specification | Nature | Priority | Responsibility | Deliverable Date | Remarks
Item Master | Need to add one field In item master for incentive calculation Applicable Yes/No | New Functionality | P1 | Chandresh | 16th June 2022 | Done
| Need to add one field in item master for BIN Required Yes/NO | New Functionality | P1 | Chandresh | 16th June 2022 | Done
| In Item master one field need to add field to capture the Lead days | New Functionality | P1 | Chandresh | 16th June 2022 | Done
| Need to add one field In item master for Warranty Applicable Yes/No and Warranty Period which is changable | New Functionality | P1 | Chandresh | 16th June 2022 | Done
| Need to add one field in Item Master should be having 2 name for the product 1 for the purchase purpose and 1 for the sales purpose | New Functionality | P1 | Chandresh | 16th June 2022 | No Need
| Need to add one field in item Master for "Shelf Life" | New Functionality | P1 | Chandresh | 16th June 2022
| In Item Master field need to add a field for "License Number" | New Functionality | P1 | Chandresh | 16th June 2022 | No Need
| In item master HSN Code 8 Digit need to fix | New Functionality | P1 |  |  | No Need to address
Returnable Gate Pass | While receiving the goods against RGP there should be 1 field list item "Fresh", "Defective" while receiving and there should be option to relocate the stock in mutiple store. This form should be available on mobile App for the engineer. "Docket number". | New Functionality | P1 | Chandresh | 17th June 2022 | Done
| In RGP we need to add "Requisition number" field for which RGP required need tracking for In-warranty so that we can track that RGP with that requistion number. | New Functionality | P1 | Chandresh |  | Done
| Need to add one filed to capture the "Employee name" while creating the RGP. | New Functionality | P1 | Chandresh | 17th June 2022 | Done
| Need to add one field In RGP to capture "Required Return Date", "Employee Name" | New Functionality | P1 | Chandresh | 17th June 2022 | Done
GRN | Excel Upload option needed in GRN | New Functionality | P1 | Jay | 23rd June 2022
| Bin Required field needed in Item master and same should ask in GRN if Bin is yes a | New Functionality | P1 | Chandresh | 18th June 2022
| Serial number field need to capture while doing the GRN | New Functionality | P1 |  |  | Already done in Barcode IN screen
| At the time of GRN need to enter Expiry date for calculating the Shelf life | New Functionality | P1 | Chandresh | 18th June 2022
Stock Ledger | In Stock report system should give the "RGP Stock" filter in stock ledger. | New Functionality | P1 | Tejinder | 17th June 2022 | Need 1 column in Stock Overhead Report
| Classification, Group, Subgroup report option need to generate for stock report need to give option for selection of all the parameter | New Functionality | P1 | Tejinder | 17th June 2022 | Parameter need to be added in Report
Non Moving Report | Non-Moving report required "From Date" , "To Date", "Store Selection" | New Report | P1 | Jay | 27th June 2022 | New Report
RGP Report All Status | RGP report needed with all the status including following details (RGP No, RGP Date, Employee Name, Product code, Product Name, Warehouse, Qty, Value, Required Return Date, Status (Return, Pending), GRN No, GRN Date) | New Report | P1 |  |  | RGP Register already there need to check
Reorder Level Report | Need to Create one report for Reorder Level Quantity & Current Stock Quantity Company wise & Branch wise | New Report | P1 | Jay | 27th June 2022 | New Report
Cost Price Modification | Need 1 form where user can modify the Cost Value for the product in the same warehouse. Situation is prcaticaly when product is non-movable then need to change the product cost price and stock value | New Form | P1 | Chandresh | 20th June 2022 | Price change option to be given in Stock to Stock Transfer
Item Wise Detailed Stock Report | Item wise Detail Report Stock report need to add the following column "Customer/Supplier", "Purchase / Sale Price", "Closing Qty", "Closing Value", Need to add 1 field in report If Sales then salesinvoice number, If Purchase then Vendor Purchase reference number, If RGP then RGP number, If Stock general then financial number and any other transactions need to check | New Report | P1 | Tejinder | 18th June 2022 | Rate to be include in Item wise Detail report
Warehouse wise Stock Report (Matrix) | In Stock Ledger (Location wise , Product wise available quantity matrix report needed with RGP Stock in separate column) then total quantity. | New Report | P1 | Tejinder | 17th June 2022 | Repeat as Point no: 18
Requistion For RGP / NRGP | Need one form to make the request against RGP and Against NRGP. Requisition no, Requistion Date, Request User, From Department, To Store, Estimated Return Date, Remarks. (RGP form this ERA date should populate. | New Form | P1 | Chandresh |  | Done

## Purchase
Form Name | Specification | Nature | Priority | Responsibility | Deliverable Date | Remarks
Purchase Order | Need to Add aditional field on Purchase Order Report to display the Technical Specification Details as defined in the item master | New Functionality | P1 | Govind | 18th June 2022 | PO Print Format required from Unicorn
Purchase Order Ammendment | While doing the PO Amendment system should display the Ammendment number alongwith PO number in PO report | New Form | P1 | Govind | 18th June 2022
Commercial Invoice | Need to develop one form for Commercial Invoice which would be for only in Import Case After PO Authorization. Required Filed is PO No, PO Date would fetch automatically and Status column would be updated manually. | New Form | P1 | Chandresh | 22nd June 2022 | Done
| This form will come in scope after PO authorization for tracking PO with commercial invoice |  | P1 | Chandresh | 22nd June 2022 | Done
| Before Authorization of Commerical invoice user need to attach the required document system should prompt to attach the document. |  | P1 | Chandresh | 22nd June 2022 | Done
| Gate entry must have those Import PO only which is having Commercial invoice done with the relevant document attached |  | P1 | Chandresh | 22nd June 2022 | Done
Assembilng / Diassembling | Need to Develop one form for Assembling / Diassembilng the product | New Form | P1 | Chandresh | 24th June 2022 | New Screen
Import PO ETA Tracking | Need to develop one report for Import purchase order tracking which would be having the following column Supplier name, PO Number, PO Date, Item name, Quantity, Estimated Time of Arrival | New Report | P1 |  |  | IPO Register
Purchase Status | Need to develop One Report which would display all the stages for the Purchase indent, RFQ, PO, GE, GRN, QC, Purchase Bill | New Report | P1 | Jay | 29th June 2022
Item Wise Purchase | Need to develop one report for Item wise Purchase detailed which would display the total purchases has been done for the given period with all the details like "Supplier Price", "FOB". | New Report | P1 | Tejinder | 21st June 2022
PO Status | Need to provide one report where user can see the Status of the Purchase order whether it is approved or pending. Filter not required | New Report | P1 | Tejinder | 21st June 2022
Import PO Consolidated Expense | Need to develop one report for Import Purchase Order wise consolidated expense. Basic Value, Expenses, Total Value | New Report | P1 |  |  | IPI Register
Purchase Return | Need to develop one report for purchase Return Summary & Detail report with all the details | New Report | P1 |  |  | Purchase Return Report