## Finance
Form / Report Name | Functionality Needed | Nature | Priority | Responsibility | Deliverable Date | Remarks
Period Closing | Period closing or Monthly closing option required for all the module except finance would be optional | New Functionality | P1 | Shiv | 12-July | Screen Attached
Voucher Number Generation | Bank Receipt / Cash Receipt / Bank Payment / Cash Payment voucher number series generation should be separately | New Functionality | P1 | Jay | 14-July
1 | Monthly voucher number reset option required for all the module | New Functionality | P1 | Jay | 20-July
Journal Voucher | In Journal voucher form need to restrict for Bank GL to subledger | New Functionality | P1
1 | Payroll after salary process and finance post then there should be auto JV and auto payment without approval | New Functionality | P2
Receipt Voucher | PDC Date, Customer Name, Cheque no, Amount, Bank, Bank Address, Remarks1, Remarks2 (For PDC) | New Functionality | P1 | Tejinder | 13-July | PDC Flag need to add. To handle the PDC we need to add 3 column. 1 is PDCYN, PDC Date, ClearPDC. ECH Flag need to hadd. To handle the ECH we need to add 3 column. 1 is ECHYN, ECH Date, Clear ECH
1 | PDC / ECH voucher should be auto vocuher in bank after unchecked | New Functionality | P1 |  |  | Alert Need to handle
2 | CANCEL option not require in Receipt Voucher as per management decision | New Functionality | P1
3 | PDC / ECH voucher when reached on the actual date then system should pass auto voucher on that particular date. Those Voucher Required Approval | New Functionality | P1 |  |  | Alert Need to handle
4 | Exchange Flactuation need to capture | New Functionality | P1 | Tejinder | 15-July
5 | Receipt voucher form if in USD then exchange rate field need to add | New Functionality | P1 | Tejinder | 13-July
Payment Voucher | In Receipt & Payment voucher form need to add List item to selecte whether the payment is Loan/Advance/Medical there should be report also to see the the detail based on the filter | New Functionality | P1 | Tejinder | 15-July | Need to add 1 filed for Reference Type dropdown. Value would be Loan/Advance/Medical/Conveyance. By default ADVANCE would be selected in case of ON-ACCOUNT.
2 | CANCEL option not require in Payment Voucher as per management decision | New Functionality | P1
3 | Exchange Flactuation need to capture | New Functionality | P1 | Tejinder | 15-July
4 | In Payment voucher PO number option need to link | New Functionality | P1 | Tejinder | 16-July | Need to add PO Number, PO Date popup system should display only those PO which belongs to the specific vendor & PO should approve and Invoice not done.
5 | Payment voucher form if in USD then exchange rate field need to add | New Functionality | P1 | Tejinder | 16-July
Fixed Deposit | FD Issue Bank Name, Maturity Date, In-Favour, BG number Applicable if yes number else unchecked, Principal Amount, Rate of Interest, (Quarterly, Monthly,On-Maturity). This field need to add on Payment voucher when FD selected. (Need to link this with Tender & optional) | New Form | P1 | Chandresh | 14-July | In Bank master need to add 1 more item in list for FD. Receipt and payment voucher form need to query in bank popup there should not display the FD account.
FD Report | Maturity Report needed | New Report | P1 | Govind | 16-July
2 | Need to provide report for the FD with interest rate accumulation on principal amount like bank |  | P1 | Govind | 16-July
General Ledger Detailed Report | If one customer or supplier is having two type of Expenses, Receipt like sales & services then there should be option to see the specific ledger type wise and entries also accordingly. | New Functionality | P1 | Tejinder | 16-July | Need to add 1 field which will contain 1 list item in grid "Sales/Service" in Receipt voucher. Debit note screen also will modify.
2 | Service & Sales invoice and balance should be display separately and consolidated as well at any point of time |  | P1 | Chandresh | 20-July
3 | In General Ledger Detailed Report need filter for whether the payment is Loan/Advance/Medical |  | p1 | Chandresh | 20-July
4 | Sub Ledger filter need to provide on Ledger report |  | P1 | Chandresh | 20-July
5 | Multi Currency Ledger need to diplay if Supplier is USD then report can be generated in any currency. |  | P1 | Chandresh | 20-July
6 | Filter required in Financial report "Territory", "Sub-Ledger", "Employee" |  | P1 | HOLD
Vendor Ageing Report | Service Ageing & Sales Ageing should display separately for the same customer. | New Report | P1 | Jay | 25-July
2 | Ageing Report should have the slabs selection 60,90,120,180 |  | P1 | Jay | 25-July
Customer Ledger Doc Wise | Terriortry wise, Emmployee wise customer Ledger need to display | New Report | P1 | HOLD
2 | Filter required in Financial report "Territory", "Sub-Ledger", "Employee" |  | P1 | HOLD
Voucher Search | Voucher Search form need to add on the basis of voucher number, date, narration, amount Slabs | New Form | P1 | Chandresh | 25-July | Screen Attached
Pending Knock-off Report | Suspense Account outstanding payment which is not knock-off should display. | New Report | P1 | Chandresh | 27-July
Balance Confirmation | Balance Confirmation report needed for Customer the report layout would be provided by the client | New Report | P2
2 | Filter required in Financial report "Territory", "Sub-Ledger", "Employee" |  | P2
PDC Due Report | In PDC case system should send auto-email to the customer for before due date | New Report | P1 | Jay | 27-July
EMI Form | EMI Form need to generate. PDC Date, Customer Name, Cheque no, Amount, Bank, Bank Address, Remarks1, Remarks2 (For PDC), From Date, To Date, Frequency. | New Report | P1
Customer Followup | Those customer who is having EMI and PDC it should not consider in Followup report | New Report | P1 | Govind | 20-July
2 | IF Outstanding is 50K and PDC amount is 50K then it should display in followup report |  | P1 | Govind | 20-July
3 | Report need to develop for customer followup (Report format need to provide by Mr. Mayur) |  | P1 | Govind | 20-July
4 | Filter required in Financial report "Territory", "Sub-Ledger", "Employee" |  | P1 | HOLD
PDC Cancelled Report | If cheque cancelled or check bounce then system should send mail to the particular customer with relevant details | New Report | P1 | Jay/Govind | 30-July
EMI Due Report | If EMI due then system should send auto mail to the relevant customer | New Report | P1
Cheque Printing | Cheque Printing report | New Report | P1
Cheque deposit Printing | Cheque deposit slip report require | New Report | P1
Bankwise ROI Master | Bank Loan Interest Calculation form needed. Bankwise rate would varry | New Form | P2
Balance Sheet (Schedule 6) | Advance amount received or payment done should display in Balance sheet as Asset & Libaility like "Advance received", "Advance Payable". Need to add field for Advance in Payment/Receipt voucher | New Report | P1 | HOLD
2 | Excel Report need to download the way it is displaying in runtime |  | P1
Cost Center Expense Report | After closing the period then Cost centre expense report will calculate based on sales of same month on ratio basis | New Report | P1 | HOLD
P&L | State wise P&L | New Report | P1
2 | Department wise P&L |  | P1 | HOLD
3 | Excel Report need to download the way it is displaying in runtime |  | P1
Budget Master | Need one form to define Monthly budget | New Form | P1
2 | State, Department wise budget need to define |  | P1
Budget Report | Budget GL wise | New Report | P1 |  |  | Screen Attached
2 | Budget Vs Actual GL wise |  | P1
3 | Target vs Actual Product wise & Product value |  | P1
Bank Book | There should be Total at bottom. Voucher type should show voucher type it is showing some number | New Functionality | P1
Cash Book | There should be Total at bottom. Voucher type should show voucher type it is showing some number | New Functionality | P1
Cash flow report | Cash flow report need to design as per statuatory | New Report | P1
2 | Excel Report need to download the way it is displaying in runtime |  | P1
Fund flow report | Fund flow report need to design as per statuatory | New Report | P1
2 | Excel Report need to download the way it is displaying in runtime |  | P1
COGS Report | COGS report sales , item wise need to provide | New Report | P1
Day Book | Need to develop one report for Day Book which would include all the financial transactions | New Report | P1
2 | Excel Report need to download the way it is displaying in runtime |  | P1
Tender Report EMD / | Need to develop one report for Tender | New Report | P2
Balance Sheet (Schedule 6) | Schedule 6 format Balance sheet & P&L | New Report | P1 | HOLD

## Period_Closing
Period Closing
Transaction Lock for the period (Current Year)
From Date | To Date
Module
Form Name |  | Period Lock Type | From Date | To Date | Days
All the transactional form will appear in this detail block while selecting the module. |  | 1. Always Lock 2. No of Days 3. For the Period (From - To)
If Always Lock selected From Date, To Date, Days field will be invisible
If No of Days selected then From Date, To Date will be invisible and Days field would be enterable
If For the Period selected then Days will be invisible and From Date, To Date would be enterable

## Voucher_Number_Generation
Voucher Type | Restart Basis | Starting No
BR | Yearly
BP | Monthly
CP | Weekly
CR | Daily
JV | Carry Forward
CN

## Fixed Deposit
Fixed Deposit
FD Code
| FD Date | ¦
| Bank Account | 6 |  |  | Account Number
| FD Issued Bank Name | 6 |  |  | Account Number
| Maturity Date | ¦
In-Favour
| BG number Applicabe Y/N | 6 | BG Number |  |  | BG number Applicable if yes number required else unchecked
Principal Amount
| Rate of Interest base | 6 |  | Rate of Interest
This ROI would be Quarterly, Monthly, Yearly, On-Maturity

## Voucher Search
Voucher Search (Parent Screen) |  |  |  |  | Voucher Search (Child 1 Screen)
SEARCH
| Voucher Status | All
|  | Posted |  |  |  | Voucher Date |  | Voucher Number |  | Amount |  | Ledger Name
|  | Unposted | [10 empty] | Details
Details
| Voucher Type | 6 | [10 empty] | Details
Details
| Voucher Number From |  | Voucher Number To | [9 empty] | Details
Details
| Voucher Date From | ¦ | Voucher Date To | ¦ | [8 empty] | Details
Details
| Account Name | 6 | [10 empty] | Details
Details
| Amount From |  | Amount To | [9 empty] | Details
Details
| Cheque Number |  | Cheque Date | ¦
Voucher Search (Child 2 Screen)
| Posted By | 6
Voucher No
| Post Date From | ¦ | Post Date To | ¦
Voucher Date
Narration
[6 empty] | Sr. No | Account Name |  | Amount |  | Dr/Cr | Narration

## Budget Master
Budget Master
Financial Year | 6 |  | Budget No |  | Date | ¦ |  | ** Month column would be bind dynamically based on Financial year in common module
Account Group | GL Code | Name |  | Cost Center | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | TOTAL
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6
6 | 6 |  |  | 6