## Screen
SL No | Form Name | Module Name | Type | status
Common Module
1 | Voucher Type Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
2 | Country Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
3 | State Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
4 | City Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
5 | District Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
6 | Month Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
7 | Year Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
8 | Financial year master | COMMON MODULE | Master | Development Completed and ported on Alps Server
9 | Company Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
10 | Branch Group | COMMON MODULE | Master | Development Completed and ported on Alps Server
11 | Branch Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
12 | User Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
13 | Role Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
14 | Bank Master | COMMON MODULE | Master | Development Completed and ported on Alps Server
15 | Document Number Definition | COMMON MODULE | Master | Development Completed and ported on Alps Server
16 | Customer Coding Definition | COMMON MODULE | Master | Development Completed and ported on Alps Server
17 | Vendor Coding Definition | COMMON MODULE | Master | Development Completed and ported on Alps Server
18 | Employee Coding Definition | COMMON MODULE | Master | Development Completed and ported on Alps Server
19 | User - Role Mapping | COMMON MODULE | Master | Development Completed and ported on Alps Server
20 | Item Coding Definition | COMMON MODULE | Master | Development Completed and ported on Alps Server
21 | User-Branch Mapping | COMMON MODULE | Master | Development Completed and ported on Alps Server
22 | UDF for Branch | COMMON MODULE | UDF | Development Completed and ported on Alps Server
23 | UDF for Company | COMMON MODULE | UDF | Development Completed and ported on Alps Server
Purchase Module
24 | Vendor Group | PURCHASE MODULE | Master | Development Completed and ported on Alps Server
25 | Vendor Master | PURCHASE MODULE | Master | Development Completed and ported on Alps Server
26 | Vendor - Item Price List | PURCHASE MODULE | Master | Development Completed and ported on Alps Server
27 | Vendor - Item Info | PURCHASE MODULE | Master | Development Completed and ported on Alps Server
28 | Vendor-Branch Mapping | PURCHASE MODULE | Master | Development Completed and ported on Alps Server
29 | UDF for Vendor Master | PURCHASE MODULE | UDF | Development Completed and ported on Alps Server
30 | UDF for Vendor Quotation Management | PURCHASE MODULE | UDF | Development Completed and ported on Alps Server
31 | UDF for Purchase Order | PURCHASE MODULE | UDF | Development Completed and ported on Alps Server
32 | UDF for Blanket PO | PURCHASE MODULE | UDF | Development Completed and ported on Alps Server
33 | UDF for Service PO | PURCHASE MODULE | UDF | Development Completed and ported on Alps Server
34 | UDF for Schedule Against PO | PURCHASE MODULE | UDF | Development Completed and ported on Alps Server
35 | UDF for Schedule against Blanket PO | PURCHASE MODULE | UDF | Development Completed and ported on Alps Server
36 | Purchase Indent (PI) | PURCHASE MODULE | Transactions | Development Completed and ported on Alps Server
37 | Request for Quotation (RFQ) | PURCHASE MODULE | Transactions | Development Completed and ported on Alps Server
38 | Vendor Quotation (VQ) | PURCHASE MODULE | Transactions | Development Completed and ported on Alps Server
39 | Quotation Comparision (VQC) | PURCHASE MODULE | Transactions | Will Inform later
40 | Purchase Order (PO) | PURCHASE MODULE | Transactions | Development Completed and ported on Alps Server
41 | Purchase Order Amendment (POA) | PURCHASE MODULE | Transactions | Development Completed and ported on Alps Server
42 | Blanket Purchase Order (BPO) | PURCHASE MODULE | Transactions | Development Completed and ported on Alps Server
43 | Schedule against Blanket Purchase Order (SBP) | PURCHASE MODULE | Transactions | Development Completed and ported on Alps Server
44 | Service Purchase Order (SRPO) | PURCHASE MODULE | Transactions | Development Completed and ported on Alps Server
45 | Service Purchase Invoice (SPI) | PURCHASE MODULE | Transactions | Development Completed and ported on Alps Server
46 | Purchase Order Report | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
47 | Purchase Bill Report | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
48 | Purchase Order Print | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
49 | Purchase Indent Print | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
50 | Vendor Quotation Print | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
51 | Vendor Quotation Report | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
52 | Request for Quotation Report | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
53 | Purchase Indent Report | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
54 | Service Purchase Order Report | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
55 | Service Purchase Invoice Report | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
56 | Blanket Purchase Order Report | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
57 | Purchase Bill Register | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
58 | Material Requisition Register | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
59 | Management Mirror Report - Purchase - Item Group / Item | PURCHASE MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
Sales Module
60 | Industry Type Master | SALES MODULE | Master | Development Completed and ported on Alps Server
61 | Industry Vertical | SALES MODULE | Master | Development Completed and ported on Alps Server
62 | Customer Group | SALES MODULE | Master | Development Completed and ported on Alps Server
63 | Customer Master | SALES MODULE | Master | Development Completed and ported on Alps Server
64 | Enquiry Media Master | SALES MODULE | Master | Development Completed and ported on Alps Server
65 | Priority | SALES MODULE | Master | Development Completed and ported on Alps Server
66 | Price List Category | SALES MODULE | Master | Development Completed and ported on Alps Server
67 | Maximum Retail Price (MRP) | SALES MODULE | Master | Development Completed and ported on Alps Server
68 | Price List Standard | SALES MODULE | Master | Development Completed and ported on Alps Server
69 | Transporter Master | SALES MODULE | Master | Development Completed and ported on Alps Server
70 | Customer-Branch Mapping | SALES MODULE | Master | Development Completed and ported on Alps Server
71 | Business Unit | SALES MODULE | Master | Development Completed and ported on Alps Server
72 | Coupon Category | SALES MODULE | Master | Development Completed and ported on Alps Server
73 | Coupon Type | SALES MODULE | Master | Development Completed and ported on Alps Server
74 | Profit Centre | SALES MODULE | Master | Development Completed and ported on Alps Server
75 | UDF for Customer Master | SALES MODULE | UDF | Development Completed and ported on Alps Server
76 | UDF for Sales Enquiry | SALES MODULE | UDF | Development Completed and ported on Alps Server
77 | UDF for Sales Quotation | SALES MODULE | UDF | Development Completed and ported on Alps Server
78 | UDF for Sales Order | SALES MODULE | UDF | Development Completed and ported on Alps Server
79 | UDF for Sales Challan | SALES MODULE | UDF | Development Completed and ported on Alps Server
80 | UDF for Daily Sales Plan | SALES MODULE | UDF | Development Completed and ported on Alps Server
81 | UDF for Sales Return | SALES MODULE | UDF | Development Completed and ported on Alps Server
82 | UDF for Packing Slip | SALES MODULE | UDF | Development Completed and ported on Alps Server
83 | UDF for Sales Service Order | SALES MODULE | UDF | Development Completed and ported on Alps Server
84 | UDF for Sales Service Invoice | SALES MODULE | UDF | Development Completed and ported on Alps Server
85 | Sales Enquiry (SE) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
86 | Sales Quotation (SQ) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
87 | Sales Quotation Amendment (SQA) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
88 | Sales Order (SO) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
89 | Sales Order Amendment (SOA) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
90 | Open Sales Order (SO) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
91 | Schedule against Open Sales Order (SOS) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
92 | Daily Sales Plan (DSP) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
93 | Sales Challan (SC) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
94 | Sales Invoice (SI) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
95 | Sales Return - SR | SALES MODULE | Transactions | Development Completed and ported on Alps Server
96 | Sales Service Order (SSO) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
97 | Sales Service Invoice (SSI) | SALES MODULE | Transactions | Development Completed and ported on Alps Server
98 | Sales Order Report | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
99 | Sales Invoice Report | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
100 | Sales Enquiry Report | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
101 | Sales Quotation Report | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
102 | Sales Challan Report | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
103 | Sales Return Report | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
104 | Sales Service Order Report | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
105 | Sales Service Invoice Report | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
106 | Sales Enquiry Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
107 | Sales Quotation Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
108 | Sales Order Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
109 | Sales Plan Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
110 | Sales Challan Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
111 | Dispatch Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
112 | Receipt Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
113 | Sales Return Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
114 | Sales Forecast Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
115 | Production Forecast Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
116 | Purchase Forecast Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
117 | Sales Invoice Register | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
118 | Management Mirror Report - Sales - Item Group / Item | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
119 | Management Mirror Report - Sales Return - Item Group / Item | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
120 | Management Mirror Report - Net Sales (Sales - Return) | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
121 | Management Mirror Report - Quarterly Net Sales | SALES MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
122 | Management Mirror Report - Quarterly Net Sales (Quantity) | SALES MODULE | Print | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
123 | Management Mirror Report - Month wise Sales -Value | SALES MODULE | Print | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
124 | Sales Enquiry Print | SALES MODULE | Print | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
125 | Sales Invoice Print | SALES MODULE | Print | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
126 | Sales Challan Print | SALES MODULE | Print | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
127 | Sales Order Print | SALES MODULE | Print | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
Inventory Module
128 | Inventory Class | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
129 | Unit of Measurement (UOM) Master | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
130 | Item Category | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
131 | Store Master | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
132 | Attribute Master | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
133 | Item Group & Sub Group | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
134 | Packaging Type Master | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
135 | Cost Centre (CC) | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
136 | Item wise Opening Balance (IOB) | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
137 | Item Master | INVENTORY MODULE | Master | Development Completed and ported on Alps Server
138 | UDF for Material Requisition Slip | INVENTORY MODULE | UDF | Development Completed and ported on Alps Server
139 | UDF for Material Issue Slip | INVENTORY MODULE | UDF | Development Completed and ported on Alps Server
140 | UDF for Returnable Gate Pass (RGP) | INVENTORY MODULE | UDF | Development Completed and ported on Alps Server
141 | UDF for Non Returnable Gate Pass (NRGP) | INVENTORY MODULE | UDF | Development Completed and ported on Alps Server
142 | UDF for GE | INVENTORY MODULE | UDF | Development Completed and ported on Alps Server
143 | UDF for GRN against RGP | INVENTORY MODULE | UDF | Development Completed and ported on Alps Server
144 | UDF for GRN against GE | INVENTORY MODULE | UDF | Development Completed and ported on Alps Server
145 | UDF for Purchase Return | INVENTORY MODULE | UDF | Development Completed and ported on Alps Server
146 | UDF FOR Item Master | INVENTORY MODULE | UDF | Development Completed and ported on Alps Server
147 | Material Requisition Slip (MRS) | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
148 | Material Issue Slip (MIS) | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
149 | Non Returnable Gate Pass (NRGP) | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
150 | Gate Entry (GE) | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
151 | Goods Receipt Note against RGP | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
152 | Goods Receipt Note against GE | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
153 | Returnable Gate Pass (RGP) | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
154 | Stock Adjustment | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
155 | Store to Store Transfer | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
156 | Purchase Return | INVENTORY MODULE | Transactions | Development Completed and ported on Alps Server
157 | Physical Entry | INVENTORY MODULE | Transactions | Will Inform later
158 | Batch Wise Stock Report | INVENTORY MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
159 | NRGP Report | INVENTORY MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
160 | NRGP REGISTER | INVENTORY MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
161 | MIS Register | INVENTORY MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
162 | Gate Entry Register | INVENTORY MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
163 | GRN Register | INVENTORY MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
164 | Gate Entry Report | INVENTORY MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
165 | MRS Report | INVENTORY MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
Accounts Module
166 | Currency Master | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
167 | Currency Conversion | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
168 | GST Type | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
169 | Section Master | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
170 | NATURE OF GROUP | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
171 | Account Group | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
172 | Account Sub Group | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
173 | General Ledger Master | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
174 | HSN Master | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
175 | Tax Type Master | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
176 | Terms & Condition Template Master | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
177 | Calculation Template Master | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
178 | Sub Ledger Master | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
179 | Cost Centre (CC) Category | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
180 | Nature of Assessee | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
181 | Withholding Tax Master(TDS) | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
182 | Sales Account Set | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
183 | Purchase Account Set | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
184 | GL Opening | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
185 | SL Opening | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
186 | Custom Duty & SWS Rate - Vendor wise | ACCOUNTS MODULE | Master | Development Completed and ported on Alps Server
187 | UDF for Service Purchase Invoice | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
188 | UDF for Service Invoice landed cost | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
189 | UDF for Purchase Bill or Invoice | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
190 | UDF for Job Work Order (JWO) | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
191 | UDF for Job Work Challan (JWC) | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
192 | UDF for Gate Entry (GE) against JWO | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
193 | UDF for Goods Receipt Note (GRN) - Job Work | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
194 | UDF for Job Work Invoice (JWI) | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
195 | UDF for Job Work Return (JWR) | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
196 | UDF for Quality Inspection against GRJ (QIJ) | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
197 | UDF for AR | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
198 | UDF for AP | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
199 | UDF for GL | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
200 | UDF for SL | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
201 | UDF for BRV | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
202 | UDF for CRV | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
203 | UDF for BPV | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
204 | UDF for CPV | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
205 | UDF for JV | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
206 | UDF for PII | ACCOUNTS MODULE | UDF | Development Completed and ported on Alps Server
207 | Journal Voucher | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
208 | AR Debit Note | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
209 | AP Debit Note | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
210 | Purchase Bill / Invoice (PB) | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
211 | Import Purchase Order(IPO) | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
212 | Purchase Invoice Import (PII) | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
213 | Payment Entry Form | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
214 | Receipt Entry Form | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
215 | Landed cost | ACCOUNTS MODULE | Transactions | Will Inform later
216 | Knowk Off | ACCOUNTS MODULE | Transactions | Will Inform later
217 | Debit Note Stock and Value | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
218 | Credit Note Stock and Value | ACCOUNTS MODULE | Transactions | Development Completed and ported on Alps Server
219 | Journal Book Report | ACCOUNTS MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
220 | Bank Book Report | ACCOUNTS MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
221 | Customer Ledger Report | ACCOUNTS MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
222 | Vendor Ledger Report | ACCOUNTS MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
223 | General Ledger Report | ACCOUNTS MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
224 | Cash Book Report | ACCOUNTS MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
225 | Customer Ageing Report | ACCOUNTS MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
226 | Vendor Ageing Report | ACCOUNTS MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
227 | Trial Balance | ACCOUNTS MODULE | Report | Development Completed and ported on Alps Server
228 | Profit & Loss Report | ACCOUNTS MODULE | Report | Will Inform later
229 | Balance Sheet | ACCOUNTS MODULE | Report | Will Inform later
Production Module
230 | Production Stages | PRODUCTION MODULE | Master | Development Completed and ported on Alps Server
231 | Cost Component | PRODUCTION MODULE | Master | Development Completed and ported on Alps Server
232 | Machine wise - Mould Info | PRODUCTION MODULE | Master | Development Completed and ported on Alps Server
233 | Bill of Material (BOM) | PRODUCTION MODULE | Master | Development Completed and ported on Alps Server
234 | Amendmenet of Bill of Material (ABM) | PRODUCTION MODULE | Master | Development Completed and ported on Alps Server
235 | Machine wise - Item Info | PRODUCTION MODULE | Master | Development Completed and ported on Alps Server
236 | Routing Master | PRODUCTION MODULE | Master | Development Completed and ported on Alps Server
237 | UDF for Bill of Material (BOM) | PRODUCTION MODULE | UDF | Development Completed and ported on Alps Server
238 | UDF for Batch Card / Production Order (PRO) | PRODUCTION MODULE | UDF | Development Completed and ported on Alps Server
239 | UDF for Requisition against PRO (RPR) | PRODUCTION MODULE | UDF | Development Completed and ported on Alps Server
240 | UDF for Material Issue Slip (PMIS) | PRODUCTION MODULE | UDF | Development Completed and ported on Alps Server
241 | UDF for Production & Movement (PNM) | PRODUCTION MODULE | UDF | Development Completed and ported on Alps Server
242 | UDF for Return from Production Floor (RPF) | PRODUCTION MODULE | UDF | Development Completed and ported on Alps Server
243 | UDF for Material Issue Slip against RPR (MISR) | PRODUCTION MODULE | UDF | Development Completed and ported on Alps Server
244 | Production Order (PRO) | PRODUCTION MODULE | Transactions | Development Completed and ported on Alps Server
245 | Requisition against PRO (RPR) | PRODUCTION MODULE | Transactions | Development Completed and ported on Alps Server
246 | Material Issue Slip against RPR (MISR) | PRODUCTION MODULE | Transactions | Development Completed and ported on Alps Server
247 | Production & Movement(PNM) | PRODUCTION MODULE | Transactions | Development Completed and ported on Alps Server
248 | Daily Production Plan | PRODUCTION MODULE | Transactions | Development Completed and ported on Alps Server
249 | Production Order Report | PRODUCTION MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
250 | Production & Movement Report | PRODUCTION MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
251 | Daily Production Plan Register | PRODUCTION MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
252 | Requisition against PRO Register | PRODUCTION MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
253 | Material Issue Slip against RPR Register | PRODUCTION MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
254 | BOM Checklist | PRODUCTION MODULE | Report | Development Completed and ported on Alps Server | Changes asked by ALPS in Process
Payroll Module
251 | Pay Period | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
252 | Employee Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
253 | Shift Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
254 | Post Level | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
255 | Designation Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
256 | Grade Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
257 | Gender Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
258 | Employee Category | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
259 | Employee Type | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
260 | Project Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
261 | Salutation Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
262 | Department Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
263 | Division Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
264 | Blood Group Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
265 | Relationship Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
266 | Earning Head Type | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
267 | Earning Head | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
268 | Deduction Head Type | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
269 | Deduction Head | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
270 | Salary Structure Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
271 | Calculation Basis (Applicable) | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
272 | Attendance Status | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
273 | Type of Holiday | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
274 | Leave Type | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
275 | Loan Type | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
276 | OT Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
277 | Bonus Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
278 | Gratuity Master | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
279 | Leave Encashment Provision | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
280 | Employee-Branch Mapping | PAYROLL MODULE | Master | Development Completed and ported on Alps Server
Quality Module
281 | QC Parameter Master | QUALITY MODULE | Master | Development Completed and ported on Alps Server
282 | Rejection Reason Master | QUALITY MODULE | Master | Development Completed and ported on Alps Server
283 | UDF for Quality Inspection (QI) | QUALITY MODULE | UDF | Development Completed and ported on Alps Server
284 | UDF for Quality Inspection Deviation (QID) | QUALITY MODULE | UDF | Development Completed and ported on Alps Server
285 | UDF for Quality Inspection WIP (QIW) | QUALITY MODULE | UDF | Development Completed and ported on Alps Server
286 | UDF for Pre-Dispatch Inspection (PDI) | QUALITY MODULE | UDF | Development Completed and ported on Alps Server
Plant Maintenance Module
287 | Fuel Type | PLANT MAINTENANCE MODULE | Master | Development Completed and ported on Alps Server
288 | Machine Master | PLANT MAINTENANCE MODULE | Master | Development Completed and ported on Alps Server
289 | Energy Meter Master | PLANT MAINTENANCE MODULE | Master | Development Completed and ported on Alps Server
290 | Maintenance Parameter (MP) | PLANT MAINTENANCE MODULE | Master | Development Completed and ported on Alps Server
291 | Maintenance Sub Parameter (MSP) | PLANT MAINTENANCE MODULE | Master | Development Completed and ported on Alps Server
292 | UDF for Import Purchase Order(IPO) | PLANT MAINTENANCE MODULE | Master | Development Completed and ported on Alps Server
293 | Maintenance Checklist | PLANT MAINTENANCE MODULE | Master | Development Completed and ported on Alps Server
294 | Machine wise Checklist | PLANT MAINTENANCE MODULE | Master | Development Completed and ported on Alps Server
Annual Forecast Module
295 | Annual Forecast Sales (AFS) | FORECAST & MRP MODULE | Transactions | Development Completed and ported on Alps Server
296 | Annual Forecast Purchase (AFP) | FORECAST & MRP MODULE | Transactions | Development Completed and ported on Alps Server
294 | Annual Forcast Production | FORECAST & MRP MODULE | Transactions | Will Inform later

## Backup (hidden)
67 | Stock Ledger | PURCHASE MODULE | Report
68 | UDF for Bill of Material (BOM) | PRODUCTION MODULE | UDF
69 | UDF for Batch Card / Production Order (PRO) | PRODUCTION MODULE | UDF
70 | UDF for Requisition against PRO (RPR) | PRODUCTION MODULE | UDF
71 | UDF for Material Issue Slip (PMIS) | PRODUCTION MODULE | UDF
72 | UDF for Production & Movement (PNM) | PRODUCTION MODULE | UDF
73 | UDF for Return from Production Floor (RPF) | PRODUCTION MODULE | UDF
74 | Production Stages | PRODUCTION MODULE | Master
75 | Cost Component | PRODUCTION MODULE | Master
76 | Machine wise - Mould Info | PRODUCTION MODULE | Master
77 | Bill of Material (BOM) | PRODUCTION MODULE | Master
78 | Amendmenet of Bill of Material (ABM) | PRODUCTION MODULE | Master
79 | Machine wise - Item Info | PRODUCTION MODULE | Master
80 | Production Order (PRO) | PRODUCTION MODULE | Transactions
81 | Routing Master | PRODUCTION MODULE | Master
82 | Requisition against PRO (RPR) | PRODUCTION MODULE | Transactions
83 | UDF for Material Issue Slip against RPR (MISR) | PRODUCTION MODULE | UDF
84 | Material Issue Slip against RPR (MISR) | PRODUCTION MODULE | Transactions
85 | UDF for Quality Inspection (QI) | QUALITY MODULE | UDF
86 | UDF for Quality Inspection Deviation (QID) | QUALITY MODULE | UDF
87 | UDF for Quality Inspection WIP (QIW) | QUALITY MODULE | UDF
88 | UDF for Pre-Dispatch Inspection (PDI) | QUALITY MODULE | UDF
89 | QC Parameter Master | QUALITY MODULE | Master
90 | Rejection Reason Master | QUALITY MODULE | Master
91 | Customer Master | SALES MODULE | Master
92 | UDF for Sales Quotation | SALES MODULE | UDF
93 | UDF for Customer Master | SALES MODULE | UDF
94 | Business Unit | SALES MODULE | Master
95 | UDF for Daily Sales Plan | SALES MODULE | UDF
96 | UDF for Sales Challan | SALES MODULE | UDF
97 | UDF for Sales Return | SALES MODULE | UDF
98 | UDF for Packing Slip | SALES MODULE | UDF
99 | UDF for Sales Order | SALES MODULE | UDF
100 | Enquiry Media Master | SALES MODULE | Master
101 | Priority | SALES MODULE | Master
102 | Industry Type Master | SALES MODULE | Master
103 | Industry Vertical | SALES MODULE | Master
104 | Coupon Category | SALES MODULE | Master
105 | Coupon Type | SALES MODULE | Master
106 | Price List Category | SALES MODULE | Master
107 | Maximum Retail Price (MRP) | SALES MODULE | Master
108 | Profit Centre | SALES MODULE | Master
109 | Transporter Master | SALES MODULE | Master
110 | Sales Enquiry (SE) | SALES MODULE | Transactions
111 | Sales Quotation (SQ) | SALES MODULE | Transactions
112 | Sales Quotation Amendment (SQA) | SALES MODULE | Transactions
113 | Sales Order (SO) | SALES MODULE | Transactions
114 | Sales Order Amendment (SOA) | SALES MODULE | Transactions
115 | Open Sales Order (SO) | SALES MODULE | Transactions
116 | Schedule against Open Sales Order (SOS) | SALES MODULE | Transactions
117 | Daily Sales Plan (DSP) | SALES MODULE | Transactions
118 | Sales Challan (SC) | SALES MODULE | Transactions
119 | Sales Invoice (SI) | SALES MODULE | Transactions
120 | Sales Return - SR | SALES MODULE | Transactions
121 | UDF for Sales Enquiry | SALES MODULE | UDF
122 | UDF for Sales Service Order | SALES MODULE | UDF
123 | UDF for Sales Service Invoice | SALES MODULE | UDF
124 | Customer Group | SALES MODULE | Master
125 | Customer-Branch Mapping | SALES MODULE | Master
126 | Price List Standard | SALES MODULE | Master
127 | Sales Service Order (SSO) | SALES MODULE | Transactions
128 | Sales Service Invoice (SSI) | SALES MODULE | Transactions
129 | Sales Order Report (SLOR) | SALES MODULE | Report
130 | Sales Order Summary-SO No Wise | SALES MODULE | Report
131 | Dispatch Summary-SI No Wise | SALES MODULE | Report
132 | Sales Order Summary-Item Wise | SALES MODULE | Report
133 | Dispatch Summary-Item Wise | SALES MODULE | Report
134 | Sales Order Summary-SL Wise | SALES MODULE | Report
135 | Dispatch Summary-SL Wise | SALES MODULE | Report
136 | Sales Order Summary-Sales Person Wise | SALES MODULE | Report
137 | Dispatch Summary-Sales Person Wise | SALES MODULE | Report
138 | Sales Order Summary-City Wise | SALES MODULE | Report
139 | Dispatch Summary-City Wise | SALES MODULE | Report
140 | Sales Order Summary-Country Wise | SALES MODULE | Report
141 | Dispatch Summary-Country Wise | SALES MODULE | Report
142 | Sales Order Summary-State Wise | SALES MODULE | Report
143 | Dispatch Summary-State Wise | SALES MODULE | Report
144 | Sales Enquiry Register | SALES MODULE | Report
145 | Sales Quotation Register | SALES MODULE | Report
146 | Sales Order Register | SALES MODULE | Report
147 | Sales Plan Register | SALES MODULE | Report
148 | Sales Challan Register | SALES MODULE | Report
149 | Dispatch Register | SALES MODULE | Report
150 | Receipt Register | SALES MODULE | Report
151 | Sales Return Register | SALES MODULE | Report
152 | Sales Forecast Register | SALES MODULE | Report
153 | Production Forecast Register | SALES MODULE | Report
154 | Purchase Forecast Register | SALES MODULE | Report
155 | Sales Invoice Register | SALES MODULE | Report
156 | Management Mirror Report - Sales - Item Group / Item | SALES MODULE | Report
157 | Management Mirror Report - Sales Return - Item Group / Item | SALES MODULE | Report
158 | Management Mirror Report - Net Sales (Sales - Return) | SALES MODULE | Report
159 | Management Mirror Report - Quarterly Net Sales | SALES MODULE | Report
160 | Management Mirror Report - Quarterly Net Sales (Quantity) | SALES MODULE | Report
161 | Management Mirror Report - Month wise Sales -Value | SALES MODULE | Report
162 | Sales Enquiry Print | SALES MODULE | Report
163 | Sales Invoice Print | SALES MODULE | Report
164 | Sales Challan Print | SALES MODULE | Report
165 | Sales Order Print | SALES MODULE | Report
166 | Fuel Type | PLANT MAINTENANCE MODULE | Master
167 | Machine Master | PLANT MAINTENANCE MODULE | Master
168 | Energy Meter Master | PLANT MAINTENANCE MODULE | Master
169 | Maintenance Parameter (MP) | PLANT MAINTENANCE MODULE | Master
170 | Maintenance Sub Parameter (MSP) | PLANT MAINTENANCE MODULE | Master
171 | Maintenance Checklist | PLANT MAINTENANCE MODULE | Master
172 | Machine wise Checklist | PLANT MAINTENANCE MODULE | Master
173 | UDF FOR Item Master | INVENTORY MODULE | UDF
174 | Item wise Opening Balance (IOB) | INVENTORY MODULE | Master
175 | Attribute Master | INVENTORY MODULE | Master
176 | Item Master | INVENTORY MODULE | Master
177 | Unit of Measurement (UOM) Master | INVENTORY MODULE | Master
178 | Item Group & Sub Group | INVENTORY MODULE | Master
179 | Item Category | INVENTORY MODULE | Master
180 | Store Master | INVENTORY MODULE | Master
181 | Packaging Type Master | INVENTORY MODULE | Master
182 | UDF for Material Requisition Slip | INVENTORY MODULE | UDF
183 | UDF for Material Issue Slip | INVENTORY MODULE | UDF
184 | UDF for Returnable Gate Pass (RGP) | INVENTORY MODULE | UDF
185 | UDF for Non Returnable Gate Pass (NRGP) | INVENTORY MODULE | UDF
186 | UDF for GE | INVENTORY MODULE | UDF
187 | UDF for GRN against RGP | INVENTORY MODULE | UDF
188 | UDF for GRN against GE | INVENTORY MODULE | UDF
189 | UDF for Purchase Return | INVENTORY MODULE | UDF
190 | UDF for Service Receipt Note (SRN) | INVENTORY MODULE | UDF
191 | Material Requisition Slip (MRS) | INVENTORY MODULE | Transactions
192 | Material Issue Slip (MIS) | INVENTORY MODULE | Transactions
193 | Non Returnable Gate Pass (NRGP) | INVENTORY MODULE | Transactions
194 | Gate Entry (GE) | INVENTORY MODULE | Transactions
195 | Inventory Class | INVENTORY MODULE | Master
196 | Returnable Gate Pass (RGP) | INVENTORY MODULE | Transactions
197 | Goods Receipt Note against RGP | INVENTORY MODULE | Transactions
198 | Goods Receipt Note against GE | INVENTORY MODULE | Transactions
199 | Cost Centre (CC) | INVENTORY MODULE | Master
200 | Stock Adjustment | INVENTORY MODULE | Transactions
201 | Store to Store Transfer | INVENTORY MODULE | Transactions
202 | Batch Wise Stock Report | INVENTORY MODULE | Report
203 | NRGP Summary Item Group Wise | INVENTORY MODULE | Report
204 | NRGP SUMMARY REGISTER | INVENTORY MODULE | Report
205 | NRGP Summary Vendor Wise | INVENTORY MODULE | Report
206 | Calculation Template Master | ACCOUNTS MODULE | Master
207 | NATURE OF GROUP | ACCOUNTS MODULE | Master
208 | General Ledger Master | ACCOUNTS MODULE | Master
209 | Terms & Condition Template Master | ACCOUNTS MODULE | Master
210 | UDF for Service Purchase Invoice | ACCOUNTS MODULE | UDF
211 | UDF for Service Invoice landed cost | ACCOUNTS MODULE | UDF
212 | UDF for Purchase Bill or Invoice | ACCOUNTS MODULE | UDF
213 | UDF for Job Work Order (JWO) | ACCOUNTS MODULE | UDF
214 | UDF for Job Work Challan (JWC) | ACCOUNTS MODULE | UDF
215 | UDF for Gate Entry (GE) against JWO | ACCOUNTS MODULE | UDF
216 | UDF for Goods Receipt Note (GRN) - Job Work | ACCOUNTS MODULE | UDF
217 | UDF for Quality Inspection against GRJ (QIJ) | ACCOUNTS MODULE | UDF
218 | UDF for Job Work Invoice (JWI) | ACCOUNTS MODULE | UDF
219 | UDF for Job Work Return (JWR) | ACCOUNTS MODULE | UDF
220 | Account Group | ACCOUNTS MODULE | Master
221 | Account Sub Group | ACCOUNTS MODULE | Master
222 | Sub Ledger Master | ACCOUNTS MODULE | Master
223 | Cost Centre (CC) Category | ACCOUNTS MODULE | Master
224 | Currency Master | ACCOUNTS MODULE | Master
225 | GST Type | ACCOUNTS MODULE | Master
226 | Tax Type Master | ACCOUNTS MODULE | Master
227 | Currency Conversion | ACCOUNTS MODULE | Master
228 | HSN Master | ACCOUNTS MODULE | Master
229 | Section Master | ACCOUNTS MODULE | Master
230 | Nature of Assessee | ACCOUNTS MODULE | Master
231 | Sales Account Set | ACCOUNTS MODULE | Master
232 | Withholding Tax Master(TDS) | ACCOUNTS MODULE | Master
233 | Purchase Account Set | ACCOUNTS MODULE | Master
234 | Journal Voucher | ACCOUNTS MODULE | Transactions
235 | UDF for GL | ACCOUNTS MODULE | UDF
236 | UDF for SL | ACCOUNTS MODULE | UDF
237 | UDF for BRV | ACCOUNTS MODULE | UDF
238 | UDF for CRV | ACCOUNTS MODULE | UDF
239 | UDF for BPV | ACCOUNTS MODULE | UDF
240 | UDF for CPV | ACCOUNTS MODULE | UDF
241 | UDF for JV | ACCOUNTS MODULE | UDF
242 | UDF for PII | ACCOUNTS MODULE | UDF
243 | GL Opening | ACCOUNTS MODULE | Master
244 | SL Opening | ACCOUNTS MODULE | Master
245 | UDF for AR | ACCOUNTS MODULE | UDF
246 | UDF for AP | ACCOUNTS MODULE | UDF
247 | AR Debit Note | ACCOUNTS MODULE | Transactions
248 | AP Debit Note | ACCOUNTS MODULE | Transactions
249 | Purchase Bill / Invoice (PB) | ACCOUNTS MODULE | Transactions
250 | Custom Duty & SWS Rate - Vendor wise | ACCOUNTS MODULE | Master
251 | Import Purchase Order(IPO) | ACCOUNTS MODULE | Transactions
252 | Purchase Invoice Import (PII) | ACCOUNTS MODULE | Transactions
253 | Payment Entry Form | ACCOUNTS MODULE | Transactions
254 | Receipt Entry Form | ACCOUNTS MODULE | Transactions
255 | UDF for Import Purchase Order(IPO) | ACCOUNTS MODULE | UDF
256 | Post Level | PAYROLL MODULE | Master
257 | Designation Master | PAYROLL MODULE | Master
258 | Grade Master | PAYROLL MODULE | Master
259 | Gender Master | PAYROLL MODULE | Master
260 | Employee Category | PAYROLL MODULE | Master
261 | Employee Type | PAYROLL MODULE | Master
262 | Project Master | PAYROLL MODULE | Master
263 | Salutation Master | PAYROLL MODULE | Master
264 | Pay Period | PAYROLL MODULE | Master
265 | Employee Master | PAYROLL MODULE | Master
266 | Shift Master | PAYROLL MODULE | Master
267 | Department Master | PAYROLL MODULE | Master
268 | Division Master | PAYROLL MODULE | Master
269 | Blood Group Master | PAYROLL MODULE | Master
270 | Relationship Master | PAYROLL MODULE | Master
271 | Earning Head Type | PAYROLL MODULE | Master
272 | Earning Head | PAYROLL MODULE | Master
273 | Deduction Head Type | PAYROLL MODULE | Master
274 | Deduction Head | PAYROLL MODULE | Master
275 | Attendance Status | PAYROLL MODULE | Master
276 | Type of Holiday | PAYROLL MODULE | Master
277 | Leave Type | PAYROLL MODULE | Master
278 | Loan Type | PAYROLL MODULE | Master
279 | OT Master | PAYROLL MODULE | Master
280 | Leave Encashment Provision | PAYROLL MODULE | Master
281 | Bonus Master | PAYROLL MODULE | Master
282 | Gratuity Master | PAYROLL MODULE | Master
283 | Salary Structure Master | PAYROLL MODULE | Master
284 | Calculation Basis (Applicable) | PAYROLL MODULE | Master
285 | Employee-Branch Mapping | PAYROLL MODULE | Master
286 | Annual Forecast Sales (AFS) | FORECAST & MRP MODULE | Transactions
287 | Annual Forecast Purchase (AFP) | FORECAST & MRP MODULE | Transactions

## Issues
SL No | Issues | Status
1 | Need auto coding in ERP master for entering fresh master data | Development Completed and ported on Alps Server
2 | Same branch(GST)have same series | Will take in next phase after completion of first phase
3 | Document series should close based on financial year--- Also financial master selection at the time of login the ERP(Already discussed last time with sir.) | Will give provision at the time of year closing
4 | In item master item class, item sub group and item category should not be mandatory and if we select item type as service then item class item group, item sub group, item category, BU, Store will be optional. In case ALPS all ALPS specific field would be mandatory | Development Completed and ported on Alps Server
5 | Need Purchase account set and sales account set option in item group master | Development Completed and ported on Alps Server
6 | Need cash option in bank master and master name should be bank/cash master | Development Completed and ported on Alps Server
7 | Item Name Duplicate--Currently check in item name that duplicate name not allow but in ALPS duplicate name should be allow. | Development Completed and ported on Alps Server
8 | Item Pop-up window à when select Item in any window require important field i.e. BU, Item Name, ALPS Part No., Customer no. & OEM Part No. | Development Completed and ported on Alps Server
9 | Item selection option a Select all & one by one both option require | Development Completed and ported on Alps Server
10 | Item Master listing a screen require a Item Code, Business Unit, Item Name, ALPS Part No., Customer Part no. Create date | Development Completed and ported on Alps Server
11 | Customer/Vendor/Item Master a Freeze header so that easy to identify the detail. | Development Completed and ported on Alps Server | Will provide Header row bottom of the screen also.
12 | Customer Master listing a screen require a Customer Code, Customer Name, State, GST No. & Create date | Development Completed and ported on Alps Server
13 | Vendor Master listing a screen require a Vendor Code, Vendor Name, State, GST No. & Create date | Development Completed and ported on Alps Server
14 | All Master a require to download in Excel option to review-- Will manage in Report4- ALPS Logo left top require & also require to edit option in future. | Will take in next phase after completion of first phase
15 | Alps Logo as per your suggestion. | Development Completed and ported on Alps Server
16 | Remove GL from all sales transaction form and change SL as customer. | Development Completed and ported on Alps Server
17 | Search Option à Form Search button | Will take in next phase after completion of first phase
18 | ERP Back button require.-----Means left side menu option should be fix so that we can easily identify that the open form belongs to which module | Will take in next phase after completion of first phase
19 | Back date voucher Freeze Button.----- Means for the year closing or month closing. | Will take in next phase after completion of first phase
20 | Selection with Mouse & Keyboard require. | Will take in next phase after completion of first phase
21 | Label Size looks inaccurate, please utilization space as require. | Development Completed and ported on Alps Server
22 | Price List require a Copy & Paste option because every 3 months unit price change for all products | Will take in next phase after completion of first phase
23 | Sale Order a Direct Option default require will change if with quotation or without quotation | Development Completed and ported on Alps Server | Already requirement is settled and Direct Sales Order option given
24 | Sale Invoice a Due date as per Credit days auto calculation | Development Completed and ported on Alps Server
25 | Sale Invoice a Digital signature option | Will take in next phase after completion of first phase
26 | Sale Invoice a E-invoicing | Will take in next phase after completion of first phase
27 | Sale Delivery Challan a as share format already require with email auto send option | Will take in next phase after completion of first phase
28 | Sale Invoice a E-invoicing require with auto mail once invoice final | Will take in next phase after completion of first phase
29 | HSN a Tax Description auto selection of IGST, CGST & SGST (Input & output) | Need discussion on it
30 | E-mail option are still pending | Will take in next phase after completion of first phase
31 | Approval alert in ERP with email | Will take in next phase after completion of first phase
32 | Home Page Approval pending list----Client need 1 Report of pending list for approval | Will take in next phase after completion of first phase
33 | Sale Enquiry & Sale Quotation a all editable field require due to many Items those not possible to registered in ERP & not require with Sale Order. | Will take in next phase after completion of first phase
34 | Attachment file are mandatory before save the Transaction | Not Possible
35 | Select option instead of double click in Popups in all the screens. | Development Completed and ported on Alps Server
36 | Item Popup working properly on Alps Server as Reported by Mr. Rajiv | Development Completed and ported on Alps Server