## HR-Payroll
Menu | Sr. No | Form / Report Name | Layout Designed | Development Status | Development Responsibility | Deliverable Date | Testing Status | Testing Responsibility
Masters | 1 | Pay Period | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 2 | Employee Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 3 | Shift Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 4 | Post Level | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 5 | Designation Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 6 | Grade Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 7 | Gender Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 8 | Employee Category | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 9 | Employee Type | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 10 | Project Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 11 | Salutation Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 12 | Department Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 13 | Division Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 14 | Blood Group Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 15 | Relationship Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 16 | Earning Head Type | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 17 | Earning Head | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 18 | Deduction Head | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 19 | Deduction Head Type | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 20 | Salary Structure Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 21 | Calculation Basis (Applicable) | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 22 | Definition Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 23 | Attendance Status | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 24 | Type of Holiday | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 25 | Company Holiday | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 26 | Leave Type | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 27 | Leave Opening Balance | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 28 | Loan Type | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 29 | TDS Slabs | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 30 | Professional Tax Slab | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 31 | Labour Welfare Funds Slabs | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 32 | OT Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 33 | Bonus Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 34 | Gratuity Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 35 | ESI Rules | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 36 | GL Opening | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 37 | Leave Encashment Provision | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 38 | Employee-Branch Mapping | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 39 | Leave Rules | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 40 | Company Working Day | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
Transactions
| 1 | Assign Leave | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 2 | Leave Approval | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 3 | Adjustment Voucher - Head wise | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 4 | Loan Disbursement | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 5 | Employee Declaration | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 6 | Reimbursement | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 7 | Leave Apply | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 8 | Claim Form | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 9 | Provision of Bonus & Gratuity | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 10 | Full & Final Settlement | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 11 | Adjustment Voucher - Employee wise | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Vinay
| 12 | Final Attendance | Yes | Pending | Mr. Tejinder | 29-04-2022 | Pending | Mr. Vinay
| 13 | Attendance IN/OUT | Yes | Pending | Mr. Tejinder | 29-04-2022 | Pending | Mr. Vinay
| 13 | Salary Process | Yes | Pending | Mr. Tejinder | 29-04-2022 | Pending | Mr. Vinay
Reports | 1 | Salary Register | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 2 | Salary Register Std Vs Actual | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 3 | Salary Summary | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 4 | PF Month Summary | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 5 | PF Annual Month wise Employee Summary | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 6 | Yearly Month wise PF Summary | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 7 | PF Month-Head wise Summary | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 8 | ESI Statement | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 9 | TDS Deduction Summary | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 10 | TDS Deduction Details | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 11 | PT Deduction Annual | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 12 | LWF Deduction Annual | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 13 | Leave Register | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 14 | Leave Summary | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 15 | Payslip | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 16 | Head Count Summary | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 17 | Head Count Summary - Annual Month | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 18 | Bonus Register | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 19 | OT Register | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 20 | Gratutiy | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 21 | Loan Summary | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 22 | Loan Register | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 23 | Head-Count Yearly Month Wise | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 24 | PF Yearly - Month Wise | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay
| 25 | LWF Yearly - Month Wise | Yes | Pending | Mr. Jay / Mr. Tejinder | 23-May-2022 | Pending | Mr. Vinay

## PreSales
Menu | Sr. No | Form / Report Name | Layout Designed | Development Status | Development Responsibility | Deliverable Date | Testing Status | Testing Responsibility | Form ID | VTID
Masters | 1 | Industry Type | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Ravi
| 2 | Lead Source | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Ravi
| 3 | Lead Status | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
| 4 | Activity Type | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
| 5 | Response Type | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
| 6 | Task Type | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
| 7 | Priority Master | Yes | Done | Not Applicable | Not Applicable | Pending | Mr. Ravi
| 8 | Task Status | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
| 9 | Opportunity Type | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
| 10 | Opportunity Stage | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
| 11 | Employee Target Master | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
Transactions
| 1 | Lead Generation | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
| 2 | Opportunity | Yes | Pending | Mr. Shiv | 31-May-2021 | Pending | Mr. Ravi
Reports | 1 | Lead Register BranchWise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 456 | 526
| 2 | Lead Register TeamWise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 457 | 527
| 3 | Lead Register EmployeeWise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 458 | 528
| 4 | Lead Register SourceOf_EnquiryWise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 459 | 529
| 5 | Lead Register RFQ Details | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 460 | 530
| 6 | Lead Register Enquiry MasterSheet | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 461 | 531
| 7 | Lead Register DSRReports | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 462 | 532
| 8 | Lead Register Under Process Reports | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 463 | 533
| 9 | Lead Register Employee Consolidated | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 464 | 534
| 10 | Lead Register Lead LifeTime | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 465 | 535
| 11 | Lead Register ActiveSheet | Yes | Discardet | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 466 | 536
| 12 | Opportunity Register BranchWise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 467 | 537
| 13 | Opportunity Register TeamWise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 468 | 538
| 14 | Opportunity Register EmployeeWise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 469 | 539
| 15 | Opportunity Register SourceOfEnquiryWise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 470 | 540
| 16 | Opportunity Register DateWise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 471 | 541
| 17 | Opportunity Settlement Register | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 472 | 542
| 18 | Lead Converted to Opportunties Branch Wise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 473 | 543
| 19 | Lead Converted to Opportunties Team Wise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 474 | 544
| 20 | Lead Converted to Opportunties Employee Wise | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 475 | 545
| 21 | Prospective Customer Register | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 476 | 546
| 22 | Activity Register | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 477 | 547
| 23 | Task Register | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 478 | 548
| 24 | Sales ForeCast By Branch | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 479 | 549
| 25 | Sales ForeCast By Employee | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 480 | 550
| 26 | Target Vs Achievement Register By Employee | Yes | Pending | Mr. Chandresh / Mr. Govind | 31-May-2021 | Pending | Mr. Ravi | 481 | 551

## Sheet1
insert into TBL_MST_FORM_VOUCHER_MAP values( | 456 | 526 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(456,526,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 457 | 527 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(457,527,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 458 | 528 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(458,528,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 459 | 529 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(459,529,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 460 | 530 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(460,530,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 461 | 531 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(461,531,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 462 | 532 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(462,532,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 463 | 533 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(463,533,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 464 | 534 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(464,534,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 465 | 535 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(465,535,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 466 | 536 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(466,536,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 467 | 537 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(467,537,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 468 | 538 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(468,538,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 469 | 539 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(469,539,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 470 | 540 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(470,540,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 471 | 541 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(471,541,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 472 | 542 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(472,542,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 473 | 543 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(473,543,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 474 | 544 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(474,544,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 475 | 545 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(475,545,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 476 | 546 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(476,546,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 477 | 547 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(477,547,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 478 | 548 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(478,548,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 479 | 549 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(479,549,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 480 | 550 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(480,550,NULL,NULL,getdate(),6,4,2,'A')
insert into TBL_MST_FORM_VOUCHER_MAP values( | 481 | 551 | ,NULL,NULL,getdate(),6,4,2,'A') | insert into TBL_MST_FORM_VOUCHER_MAP values(481,551,NULL,NULL,getdate(),6,4,2,'A')

## Post-Sales(CRM)
Menu | Sr. No | Form / Report Name | Layout Designed | Development Status | Development Responsibility | Deliverable Date | Testing Status | Testing Responsibility
Transactions | 1 | Complaint Registration | No | Pending
| 2 | Complaint Re-Allocation | No | Pending
| 3 | Service Job Card | No | Pending
| 4 | AMC Proposal | No | Pending
| 5 | AMC Registration | No | Pending
| 6 | CAMC Proposal | No | Pending
| 7 | CAMC Registration | No | Pending
| 8 | Operation & Maint. Proposal | No | Pending
| 9 | Operation & Maint. Registration | No | Pending
| 10 | Preventive Maintenance Allocation | No | Pending
| 11 | Preventive Maintenance Job Card | No | Pending
Reports | 1 | Complaint Received | No | Pending
| 2 | Complaint Status | No | Pending
| 3 | Collection Detail | No | Pending
| 4 | DSR | No | Pending
| 5 | Warranty | No | Pending
| 6 | AMC / CMC Expire | No | Pending
| 7 | Pending Complaints | No | Pending
| 8 | Productivity Report | No | Pending
| 9 | AMC / CMC Proposal & Registration | No | Pending
| 10 | Happy Calling | No | Pending
| 11 | Pending Complaint | No | Pending
| 12 | Payment Received Engineer wise | No | Pending
| 13 | Spare parts in Transit | No | Pending

## Chart
DAYS
| 25 | 26 | 27 | 28 | 29 | 2 | 3 | 4 | 5 | 6 | 7 | 9 | 10 | 11 | 12 | 13 | 14 | 16 | 17 | 18 | 19 | 20 | 21 | 23 | 24 | 25 | 26 | 27 | 30 | 31
Tejinder
Ravi
Vinay
Govind
Jay
Chandresh
Shiv

## Sheet2
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 526 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,526,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 527 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,527,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 528 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,528,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 529 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,529,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 530 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,530,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 531 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,531,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 532 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,532,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 533 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,533,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 534 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,534,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 535 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,535,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 536 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,536,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 537 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,537,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 538 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,538,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 539 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,539,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 540 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,540,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 541 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,541,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 542 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,542,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 543 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,543,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 544 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,544,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 545 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,545,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 546 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,546,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 547 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,547,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 548 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,548,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 549 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,549,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 550 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,550,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518
insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF, | 551 | ,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518 | insert into TBL_MST_ROLEDETAILS(ROLLID_REF,VTID_REF,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],ATTECHMENT,INDATE) select ROLLID_REF,551,[ADD],EDIT,CANCEL,[VIEW],APPROVAL1,APPROVAL2,APPROVAL3,[PRINT],1,INDATE from TBL_MST_ROLEDETAILS a where a.VTID_REF = 518